WPDES Permit (MAMSWaP) 2026 Annual Information and Education Work Plan for __________________________Dane County, WI

Topic Areas Covered: ____________________________________________________________________________________________

Active Delivery Mechanisms Used*: ________________________________________________________________________________

* Per guidance from WDNR, MAMSWaP members may take credit for active mechanisms organized by MAMSWaP as long as they promote those activities.

| Program/ Activity | Audience | Timing | MAMSWaP Activities | Individual Municipality Activities (Check all that will be completed in 2026) | Public Education and Outreach Topic(s) Addressed1 |
| --- | --- | --- | --- | --- | --- |
| Storm Drain Mural Program | Residential Educational | - Nov-Dec 2025 - Dec 2025-Jan 2026 - Feb 2026 - Mar-Jun 2026 - Apr-Aug 2026 - Jun-Aug 2026 - Jun-Aug 2026 - Jun-Aug 2026 | - Update and post Storm Drain Mural Grant Application on Ripple Effects web site. - Promote Storm Drain Mural Program. - Rank and select 3-4 applications for new murals and 3-4 repainted murals. - Create tailored presentations/activities, present to groups and gather design ideas. - Coordinate with local artist and partners on final design, approvals, and painting storm drain murals. - Provide partner groups with articles to promote new murals locally. - Select and coordinate 3-4 repaints of weathered murals. - Add new storm drain murals to the Storm Drain Mural Project map. | ☐Promote program and encourage partner groups to apply. ☐ Help locate suitable sites for storm drain murals. ☐ Approve storm drain mural design. | - Illicit Discharge Detection and Elimination - Pollution Prevention |
| Illicit Discharge Reporting Program | Residential Public Sector Private Sector | - Jan-Dec 2026 | - Partner with Madison Dane County Public Health to follow up on illicit discharge reports that come in through the Land and Water Resources Dept. (LWRD) reporting site. | ☐ Promote LWRD Illicit Discharge Reporting Site to residents and encourage them to report potential illicit discharges. | - Illicit Discharge Detection and Elimination - Pollution Prevention |

| Clean Sweep Collection Events | Residential | - Jan-Apr 2026, Aug-Oct 2026 - Jan-Apr 2026, Aug-Oct 2026 - Jan-Apr 2026, Aug-Oct 2026 - Jan-Apr 2026, Aug-Oct 2026 | - Partner with Dane County Waste and Renewables and participating communities to plan up to four municipal Clean Sweep Hazardous Waste Collection Events at the Clean Sweep facility. - Create a registration and voucher system for residents. - Create outreach tools for participating communities. - Coordinate Hazardous Waste Collection Events. | ☐Promote Clean Sweep Hazardous Waste Collection Event to residents using provided outreach tools. ***Limited to four MAMSWaP communities that haven’t participated in last two years. Contact SWEC, if interested. *** | - Illicit Discharge Detection and Elimination - Household Hazardous Waste Disposal - Pollution Prevention |
| --- | --- | --- | --- | --- | --- |
| Stormwater Pollution/ Prevention Education Tools | Residential Educational | - Jan-Dec 2026 - Jan-Dec 2026 - Jan-Dec 2026 - Apr-Oct 2026 | - Promote stormwater ed. tools to groups and educators. - Use stormwater ed. tools in at least 5 presentations, in-person or virtual. - Check out stormwater ed. tools to at least 5 educators/groups. - Prepare and maintain rainfall simulator samples. Educational tools include: Rainfall Simulator, Enviroscape, Stormwater Animation, Lawns and Water Quality video, Stormwater Pollution and Solutions video and Storm Drain Marking, etc. | ☐Promote stormwater ed. tools to local partners, groups and educators. ☐ Post links to virtual resources on municipal web site. ☐ Check out the Enviroscape or Rainfall Simulator to use at local event(s) or presentation(s). ☐ Provide SWEC with a local presentation opportunity along with contact information. *** Limited to 10 SWEC-led presentations per year for all MAMSWaP partners. *** | - Illicit Discharge Detection and Elimination - Household Hazardous Waste Disposal/Pet Waste Management/Vehicle Washing - Yard Waste Management/Pesticide and Fertilizer Application - Stream and Shoreline Management - Residential Infiltration - Pollution Prevention |
| Leaf-free Streets for Clean Waters | Residential Educational Private Sector | - Sept 2026 - Sept-Oct 2026 - Oct-Nov 2026 - Oct-Nov 2026 | - Update and distribute Leaf-free Streets for Clean Waters Toolkit to municipalities and groups. - Print leaf-free streets signs for municipalities, as requested. - Promote actions and rain alert system through social media, flyers, newsletter articles, signs, and presentations. - Monitor weather and issue email/text rain alerts. | ☐Promote Leaf-free Streets program, encourage residents to remove street leaves before the rain and sign up for rain alerts using provided outreach toolkit. ☐ Make signs available to residents. ☐ Engage local groups in heavy street tree areas and reward good practices. | - Yard Waste Management/Pesticide and Fertilizer Application |
| Plant Dane Native Plant Program | Residential Educational Private Sector | - Nov 2025-Jan 2026 - Feb 2026 - Feb-Mar 2026 - Feb-Mar 2026 - May-Jun 2026 | - Work with Agrecol to update plant list/order system. - Update and promote Plant Dane online order site. - Update and distribute Plant Dane Toolkit to municipalities and groups. - Sell at least 20,000 native plants through Plant Dane. - Distribute native plant orders/donations. | ☐Promote Plant Dane program and encourage residents and groups to plant native plants and build rain gardens. ☐ Provide staff to assist with Plant Dane pickup event in late May. | - Stream and Shoreline Management - Residential Infiltration - Pollution Prevention - Green Infrastructure/Low Impact Development |
| Free Native Plants for School and Community Projects (FNPSCP) Program | Residential Educational Private Sector | - Nov 2025- Dec 2026 - Dec 2025-Jan 2026 - Feb-Mar 2026 - May-Jun 2026 | - Update and post FNPSCP Grant Application. - Promote and review FNPSCP Grants. - Solicit and collect donations for at least 10 FNPSCPs. - Distribute native plant donations. | ☐Promote FNPSCP program to local schools, groups, non-profits, neighborhood associations, etc. and encourage groups to apply. ☐ Assist groups with planning and installation of gardens. ☐ Promote local projects and encourage local residents and groups to donate plants through Plant Dane order system. | - Residential Infiltration - Pollution Prevention - Green Infrastructure/Low Impact Development |
| Rain Garden Coaching Session / Workshop | Residential Educational General Public | - Feb-Mar 2026 - Feb-Mar 2026 - Feb-Mar 2026 - May-Jul 2026 | - Plan and host rain garden coaching session or workshop with at least 20 people. - Promote rain garden coaching sessions. - Coordinate registrations and create customized tools for each participant. - Offer and process plant reimbursements for participants located in MAMSWaP communities. | ☐ Promote the Rain Garden Workshop and encourage residents to sign up. ☐ Volunteer to be a trainer at the Rain Garden Workshop. | - Residential Infiltration - Pollution Prevention - Green Infrastructure/Low Impact Development |
| Adopt A Storm Drain Program (AASD) | Residential Educational | - Jan-Dec 2026 - Jan-Dec 2026 - Jan-Dec 2026 - Jan-Dec 2026 - Jan-Dec 2026 - Jan-Dec 2026 | - Coordinate with Dane County Information Management to maintain and improve AASD website. - Assist volunteers with web issues. - Supply municipalities with cleaning kit materials. - Develop outreach tools and promote program. - Develop and distribute volunteer newsletter, the Storm Drain Scoop, 3-4x/year. - Work with partner communities interested in joining the program. | ☐Participate in program and provide storm drain location data to Dane County. ☐ Distribute cleaning kits to local volunteers. ☐ Promote program locally using campaign tools through newsletters, local newspaper, mailings, web site, meetings, social media, etc. *** Contact SWEC, if interested. *** | - Illicit Discharge Detection and Elimination - Yard Waste Management/Pesticide and Fertilizer Application - Pollution Prevention |
| WI Stormwater Week | Residential Public Sector Educational | - Jan-Aug 2026 - Jun-Sept 2026 - Jun-Sept 2026 | - Participate on statewide Stormwater Collaborative Group planning team. - Develop outreach resources to promote Stormwater Week. - Plan and hold at least one local outreach event during Stormwater Week. | ☐Promote stormwater related messages and events using provided outreach tools during WI Stormwater Week. ☐ Host a local stormwater related event during WI Stormwater Week. | - Illicit Discharge Detection and Elimination - Household Hazardous Waste Disposal/Pet Waste Management/Vehicle Washing - Yard Waste Management/Pesticide and Fertilizer Application - Residential Infiltration - Pollution Prevention |
| NASECA Trainings | Construction Professionals Public Sector | - Jan-Dec 2026 - Jan-Dec 2026 - Jan-Dec 2026 | - Promote NASECA Trainings. - Provide discounts to attend trainings for MAMSWaP communities. - Encourage municipal staff and contractors to attend NASECA events. | ☐Promote NASECA Trainings to municipal staff/consultants and encourage attendance through MAMSWaP provided discounts. | - Construction Sites and Post-Construction Storm Water Management |
| WI Salt Wise Program and Salt Certification Trainings | Residential Private Sector Public Sector | - Jan-Dec 2026 - Jan-Mar 2026, Sept-Dec 2026 - Sept-Oct 2026 | - Participate on WI Salt Wise Steering Committee and attend meetings. - Collaborate with WI Salt Wise partners to promote, develop and distribute resources to reduce winter salt use. - Partner with WI Salt Wise and Dane County Highway Dept. to host in-person an Equipment Open House with at least 20 participants. | ☐Promote Salt Wise resources and practices to businesses, residents, schools, organizations, and facility managers using WI Salt Wise campaign tools. ☐ Provide Salt Wise Coordinator with a local presentation opportunity along with contact information (school district, local company, etc). ** Limited to 2 WI Salt Wise-led presentations per year for all MAMSWaP partners. *** ☐ Send municipal staff to Salt Certification Trainings. ☐ Promote Salt Certification Trainings to municipal and private winter maintenance professionals and facilities managers. ☐ Partner with Salt Wise to host a salt related training in your community and actively participate by sharing local efforts with group to reduce salt use. | - Pollution Prevention |
| Rain Barrel Sale | Residential | - Jan-Mar 2026 - Jan-Mar 2026 - Apr-Oct 2026 - Apr-Oct 2026 - Apr-Oct 2026 | - Update outreach tools to promote program. - Order rain barrels and maintain supply. - Maintain online order system to sell rain barrels. - Collect and process reimbursement requests for residents in MAMSWaP communities. - Partner with City of Middleton, Village of Deforest, and City of Stoughton to store and distribute barrels. | ☐Promote rain barrel sale and use of rain barrels using MAMSWaP outreach tools. ☐Serve as a county-wide distribution site. | 5. Residential Infiltration |
| Green Infrastructure Tour | Consultants Public Sector | - TBD - TBD - TBD - TBD | - Partner with UW to plan a Green Infrastructure Tour at UW highlighting various stormwater practices and facilities on campus. - Develop handouts describing tour stops to share with participants. - Coordinate registration and logistics. - Create outreach resources for partners to promote event. | ☐Promote Green Infrastructure Tour and encourage staff and consultants to attend. | - Construction Sites and Post Construction Storm Water Management - Green Infrastructure/Low Impact Development |
| Native Garden Learning Hub Community Gatherings | General Public Residential | - Mar-Dec 2026 - Mar-Dec 2026 - Mar-Dec 2026 | - Participate in at least 3 of 5 Native Garden Learning Hub Community Gatherings. - Staff a rain garden/downspout garden focused station. - Provide resources and individual assistance to participants looking install rain or downspout gardens. | ☐Promote Native Garden Learning Hub Community Gatherings and encourage residents to attend. | - Residential Infiltration - Pollution Prevention - Green Infrastructure/Low Impact Development |
| Green Infrastructure Demo Projects | General Public | - Apr-Oct 2026 - Apr-Oct 2026 - May-Oct 2026 | - Work with interested MAMSWaP communities/Dane County parks to install at least one demo downspout gardens, rain gardens, or rain barrels. - Create custom signage/stickers for demo projects. - Provide plants and/or rain barrels and a sign for demo projects. | ☐ Provide SWEC with potential location(s) for a demo project(s). ☐ Provide input on custom signage. ☐ Help install garden, rain barrels, and signage. *** Contact SWEC, if interested. *** | - Residential Infiltration - Pollution Prevention - Green Infrastructure/Low Impact Development |
| Nature in Session Education Programs | Educational | - Jan-Apr, Sept-Dec 2026 - Jan-Apr, Sept-Dec 2026 | - Work with Lussier Heritage Center to promote programs to schools and libraries. - Train staff on stormwater activities/lessons for various age groups. - Work with Lussier staff to review and approve requests for free programs in MAMSWaP communities. | ☐ Promote program to local schools and libraries. *** Limited to 3 free programs per MAMSWaP partner with a total maximum of 20 free programs for all MAMSWaP partners. Program cost is normally $50/class. *** | - Illicit Discharge Detection and Elimination - Household Hazardous Waste Disposal/Pet Waste Management/Vehicle Washing - Yard Waste Management/Pesticide and Fertilizer Application - Residential Infiltration - Pollution Prevention |
| On-line Native Garden/Rain Garden Course | Residential Educational General Public | - Jan-Feb 2026 - Jan-Nov 2026 - Apr-Jun 2026 - Jul-Dec 2026 | - Partner with Dane County UW-Extension to finalize list of modules to include in self-led course. - Create list and collect video, photo and graphic resources to use in course modules. - Draft proposal and contract with UW Instructional Design Team - Work with Dane County UWEX and partners to create content for individual modules. | ☐ Participate as member of the planning/development team assisting with content creation and review. | - Residential Infiltration - Pollution Prevention - Green Infrastructure/Low Impact Development |
| Check-in Meetings with MAMSWaP Communities | MAMSWaP Communities | - Jun-Sept 2026 | - Coordinate meetings with individual MAMSWaP communities to discuss what's been working/not working, and gather input on future programs/activities. | ☐Schedule and attend check-in meeting. | ALL |